## Sheet1 (hidden)
Project Tasks
Id | Level | Name | Progress | Start | Due | User | Completion Date | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk | Baseline: Start Date | Baseline: Due Date | Duration (Cal. Days) | Working Days | 05/01/2019 | 06/01/2019 | 07/01/2019 | 08/01/2019 | 09/01/2019 | 10/01/2019 | 11/01/2019 | 12/01/2019 | 13/01/2019 | 14/01/2019 | 15/01/2019 | 16/01/2019 | 17/01/2019 | 18/01/2019 | 19/01/2019 | 20/01/2019 | 21/01/2019 | 22/01/2019 | 23/01/2019 | 24/01/2019 | 25/01/2019 | 26/01/2019 | 27/01/2019 | 28/01/2019 | 29/01/2019 | 30/01/2019 | 31/01/2019 | 01/02/2019 | 02/02/2019 | 03/02/2019 | 04/02/2019 | 05/02/2019 | 06/02/2019 | 07/02/2019 | 08/02/2019 | 09/02/2019 | 10/02/2019 | 11/02/2019
pX9i7qXP7jw6Uk5sxoLX | 1 | Team Selection | 100% | 05/01/2019 | 09/01/2019 | Ganesh Kumar | 30/01/2019 | [8 empty] | 5 | 3
hqnrji04AhYpYFVRv8Qh | 1 | Project Title discussion | 100% | 10/01/2019 | 17/01/2019 | Dhilipan | 30/01/2019 | [8 empty] | 8 | 6
HQePUcmfSdeegP9UCRzh | 2 | Getting approval from Prof | 100% | 12/01/2019 | 17/01/2019 | Ganesh Kumar | 30/01/2019 | [8 empty] | 6 | 4
7HueUT2pGSBAcOcTy7Uj | 2 | Choosing and finalising topic | 100% |  |  | Ganesh Kumar | 30/01/2019
bSErp7CJBOJcDBkfaPTG | 2 | Evaluation of each topics | 100% |  |  | Chandra | 30/01/2019
oeunS8RxP0OiLgGMoWXv | 1 | Pre-Study of the project | 100% | 18/01/2019 | 22/01/2019 | Team | 30/01/2019 | [8 empty] | 5 | 3
D9Sg4pYcG0TPzw5LMIVv | 2 | Gist of IoT based Smart Mfg | 100% | 20/01/2019 | 20/01/2019 | Team | 30/01/2019 | [8 empty] | 1 | 1
wvaiHDrsLqhqACukjPqG | 1 | Brief Study on Research articles | 67% | 22/01/2019 | 30/01/2019 | Team | [9 empty] | 11 | 8
P9qG1iliqYYcoBWmiZBq | 2 | IEEE papers | 0% | 20/01/2019 | 20/01/2019 | [10 empty] | 1 | 1
dfj3Pddw1J284JNTKqi6 | 2 | Articles | 100% | 22/01/2019 | 24/01/2019 |  | 30/01/2019 | [8 empty] | 3 | 3
08rYdc72GTa4oHhjIWOq | 2 | Interesting articles | 100% | 27/01/2019 | 29/01/2019 |  | 30/01/2019 | [8 empty] | 3 | 2
6L6WCQLjaZ2x0Ljp5uuw | 1 | Project Proposal | 0% | 31/01/2019 | 31/01/2019 | [10 empty] | 1 | 1
lrzjZTWGLuWdbEtArn4A | 1 | Getting ready with Vibration & Accoustics | 0% | 01/02/2019 | 05/02/2019 | [10 empty] | 5 | 3
RJGyNMxkiQNY6bfIOLcP | 2 | FFF transform eqns. | 0% | 02/02/2019 | 03/02/2019 | [10 empty] | 2
6FwR1ZzOKgsjbZzA88tx | 2 | Time domain to freq. domain conversations | 0% | 02/02/2019 | 05/02/2019 | [10 empty] | 4 | 2
6QsJX5loKgE5zYfiWzZQ | 1 | Field study of Machinery defects | 0% | 09/02/2019 | 11/02/2019 | [10 empty] | 5 | 3
vyxHpjMIJ1Y1tBfv0wM8 | 2 | Possible visit to CNC, Milling in Campus | 0% | 07/02/2019 | 09/02/2019 | [10 empty] | 3 | 2
lKr8oN8PmhD2FroUm7up | 2 | Understanding the Machinery defect | 0%
hiJYt8TP2zte794KMbfY | 1 | Devising a Experimental Set-up to study Defects | 0%
SaSgMgzrQyVD0AwEuxdz | 2 | Selection of parameters to study | 0%
PRymxxnJWRxb6tGqVTrq | 2 | Parameters identification using hardware | 0%
Tzsp8vR4UFcodGmtOxs2 | 2 | Designing the experiment | 0%
D1IfgBZ6aTlGEXXPIcpk | 3 | Design Matrix | 0%
9DOwvofNgIndysjnJ7bv | 3 | Adapting to existing machines | 0%
ZTe1sqcyqmfHarEXX24n | 1 | Hardware implementation | 0% | [12 empty] | 1 | 1
diUo1L6D6SzEJOku7iI6 | 2 | Choosing of right hardwares | 0%
VozG4r6WSNO3x16MIJTh | 2 | Studying the datasheets of Sensors & IC used | 0% | 07/01/2019 | 07/01/2019 | [10 empty] | 1 | 1
FOs7PxCpKN51H3KRL0bB | 2 | Circuit diagram & Wiring Schema | 0%
no0SB6i3p0xO2f16KrxK | 2 | Frugal Development | 0%
8Q0OsJD7GMPIWIYtSOnV | 2 | Alt. resources mapping | 0%
byHCcabv4n1udgTjqD4v | 1 | Software Implementation | 0%
tObKoFlTkKhvS0V0K9hd | 2 | Raspberry Pi basics brush up | 0%
4hlJzjBM49hF4ypeYenk | 2 | Python code for data collection from sensors | 0%
bzy5VTDmSdzm2uq2N3Vy | 2 | GUI for displaying the results | 0%
GvJ4QhPUnuRD0JnFZCH1 | 1 | Model Setup running | 0%
rTkn8CNWVpqoYYqkvrTR | 2 | Testing using predefined data | 0%